## Sheet1
Issue ID | Process | Issue Description | Risk Rating | Status | Date Raised | Due Date | Owner | Days Open | Repeat Finding
AI-001 | Procure to Pay | Vendor master changes not independently reviewed | Medium | Closed | 2025-11-13 | 2026-02-11 | Head of Procurement | 85 | No
AI-002 | Fixed Assets | Physical verification not performed annually | High | Closed | 2025-11-17 | 2026-01-16 | Finance Controller | 70 | No
AI-003 | IT General Controls | Terminated users with active access | Medium | Closed | 2025-12-04 | 2026-03-04 | IT Head | 47 | No
AI-004 | IT General Controls | Backup restoration not tested | High | Closed | 2025-12-07 | 2026-02-05 | Security Lead | 25 | No
AI-005 | Procure to Pay | PO approved after invoice date | Medium | Closed | 2025-12-11 | 2026-03-11 | Head of Procurement | 33 | No
AI-006 | Procure to Pay | Duplicate vendor invoice paid without detection | Medium | Closed | 2025-12-21 | 2026-03-21 | Head of Procurement | 43 | No
AI-007 | IT General Controls | Terminated users with active access | Medium | Closed | 2025-12-28 | 2026-03-28 | IT Head | 18 | Yes
AI-008 | Order to Cash | Credit notes issued without second approval | High | In Progress | 2026-01-01 | 2026-03-02 | AR Manager | 272 | No
AI-009 | Order to Cash | Credit notes issued without second approval | High | In Progress | 2026-02-05 | 2026-04-06 | Head of Sales Ops | 237 | Yes
AI-010 | Fixed Assets | Disposals not removed from register | Medium | Closed | 2026-02-09 | 2026-05-10 | Plant Accountant | 65 | No
AI-011 | Fixed Assets | Disposals not removed from register | High | Closed | 2026-02-17 | 2026-04-18 | Plant Accountant | 83 | Yes
AI-012 | IT General Controls | Terminated users with active access | Low | Overdue | 2026-02-22 | 2026-06-22 | IT Head | 220 | Yes
AI-013 | IT General Controls | Terminated users with active access | Low | Closed | 2026-02-28 | 2026-06-28 | IT Head | 124 | Yes
AI-014 | Hire to Retire | Joiner onboarding checklist incomplete | Low | Overdue | 2026-03-05 | 2026-07-03 | HR Manager | 209 | No
AI-015 | Order to Cash | Revenue recognised before delivery proof | High | Closed | 2026-03-07 | 2026-05-06 | Head of Sales Ops | 53 | No
AI-016 | Fixed Assets | Disposals not removed from register | Medium | Closed | 2026-03-09 | 2026-06-07 | Finance Controller | 56 | Yes
AI-017 | Procure to Pay | Three-way match overridden without approval | Medium | Overdue | 2026-03-22 | 2026-06-20 | AP Manager | 192 | No
AI-018 | Fixed Assets | Disposals not removed from register | Critical | Closed | 2026-03-28 | 2026-04-27 | Finance Controller | 24 | Yes
AI-019 | Fixed Assets | Asset additions capitalised without approval | High | Closed | 2026-03-29 | 2026-05-28 | Finance Controller | 62 | No
AI-020 | IT General Controls | Privileged access not reviewed quarterly | Medium | Closed | 2026-04-02 | 2026-07-01 | Security Lead | 79 | No
AI-021 | Fixed Assets | Asset additions capitalised without approval | Low | Closed | 2026-04-05 | 2026-08-03 | Finance Controller | 130 | Yes
AI-022 | Procure to Pay | Vendor master changes not independently reviewed | High | Closed | 2026-04-10 | 2026-06-09 | AP Manager | 82 | Yes
AI-023 | Order to Cash | Revenue recognised before delivery proof | Low | Overdue | 2026-04-10 | 2026-08-08 | Head of Sales Ops | 173 | Yes
AI-024 | Financial Close | Close checklist sign-offs missing | High | Closed | 2026-04-10 | 2026-06-09 | Finance Controller | 26 | No
AI-025 | Procure to Pay | PO approved after invoice date | High | Closed | 2026-04-16 | 2026-06-15 | AP Manager | 51 | Yes
AI-026 | Inventory | Goods receipt posted late | Medium | In Progress | 2026-04-18 | 2026-07-17 | Supply Chain Head | 165 | No
AI-027 | Financial Close | Bank reconciliations pending beyond 30 days | High | Overdue | 2026-04-22 | 2026-06-21 | GL Lead | 161 | No
AI-028 | Fixed Assets | Physical verification not performed annually | Low | Closed | 2026-05-04 | 2026-09-01 | Finance Controller | 22 | Yes
AI-029 | Treasury | Bank signatory list outdated | High | Overdue | 2026-05-04 | 2026-07-03 | Treasury Manager | 149 | No
AI-030 | Financial Close | Manual journals posted without review | Low | Overdue | 2026-05-06 | 2026-09-03 | Finance Controller | 147 | No
AI-031 | Hire to Retire | Joiner onboarding checklist incomplete | Medium | Overdue | 2026-05-10 | 2026-08-08 | HR Manager | 143 | Yes
AI-032 | IT General Controls | Privileged access not reviewed quarterly | Medium | Overdue | 2026-05-11 | 2026-08-09 | IT Head | 142 | Yes
AI-033 | Procure to Pay | Duplicate vendor invoice paid without detection | Low | Closed | 2026-05-18 | 2026-09-15 | Head of Procurement | 90 | Yes
AI-034 | Hire to Retire | Payroll register not reconciled to GL | Medium | Closed | 2026-05-21 | 2026-08-19 | Payroll Lead | 86 | No
AI-035 | IT General Controls | Change tickets lacking UAT evidence | Low | Closed | 2026-05-27 | 2026-09-24 | Security Lead | 41 | No
AI-036 | Financial Close | Bank reconciliations pending beyond 30 days | Low | Closed | 2026-05-29 | 2026-09-26 | GL Lead | 123 | Yes
AI-037 | Inventory | Cycle count variances not investigated | High | In Progress | 2026-06-05 | 2026-08-04 | Warehouse Manager | 117 | No
AI-038 | Fixed Assets | Physical verification not performed annually | Medium | Closed | 2026-06-05 | 2026-09-03 | Finance Controller | 50 | Yes
AI-039 | Financial Close | Manual journals posted without review | Medium | Closed | 2026-06-06 | 2026-09-04 | GL Lead | 78 | Yes
AI-040 | IT General Controls | Backup restoration not tested | Medium | Overdue | 2026-06-06 | 2026-09-04 | IT Head | 116 | Yes
AI-041 | Inventory | Negative stock balances in system | Low | In Progress | 2026-06-06 | 2026-10-04 | Warehouse Manager | 116 | No
AI-042 | IT General Controls | Change tickets lacking UAT evidence | Low | Open | 2026-06-10 | 2026-10-08 | IT Head | 112 | Yes
AI-043 | Treasury | Bank signatory list outdated | Low | Closed | 2026-06-13 | 2026-10-11 | Treasury Manager | 109 | Yes
AI-044 | IT General Controls | Change tickets lacking UAT evidence | Low | Closed | 2026-06-18 | 2026-10-16 | Security Lead | 104 | Yes
AI-045 | Inventory | Obsolete stock provision not reviewed | Medium | Open | 2026-07-12 | 2026-10-10 | Warehouse Manager | 80 | No
AI-046 | Hire to Retire | Leavers retained on payroll after exit date | Medium | Closed | 2026-07-14 | 2026-10-12 | HR Manager | 78 | No
AI-047 | Financial Close | Bank reconciliations pending beyond 30 days | Medium | Closed | 2026-07-15 | 2026-10-13 | Finance Controller | 77 | Yes
AI-048 | Fixed Assets | Physical verification not performed annually | Low | Closed | 2026-07-16 | 2026-11-13 | Plant Accountant | 76 | Yes
AI-049 | Fixed Assets | Disposals not removed from register | Medium | Open | 2026-07-17 | 2026-10-15 | Plant Accountant | 75 | Yes
AI-050 | Hire to Retire | Leavers retained on payroll after exit date | Critical | Overdue | 2026-07-19 | 2026-08-18 | Payroll Lead | 73 | Yes
AI-051 | Financial Close | Close checklist sign-offs missing | Low | Open | 2026-07-21 | 2026-11-18 | GL Lead | 71 | Yes
AI-052 | Financial Close | Close checklist sign-offs missing | Medium | Open | 2026-07-23 | 2026-10-21 | GL Lead | 69 | Yes
AI-053 | Procure to Pay | Vendor master changes not independently reviewed | Critical | In Progress | 2026-07-29 | 2026-08-28 | AP Manager | 63 | Yes
AI-054 | IT General Controls | Terminated users with active access | Low | In Progress | 2026-07-30 | 2026-11-27 | IT Head | 62 | Yes
AI-055 | Procure to Pay | Vendor master changes not independently reviewed | Low | Closed | 2026-07-31 | 2026-11-28 | AP Manager | 44 | Yes
AI-056 | Order to Cash | Credit notes issued without second approval | Medium | Closed | 2026-08-01 | 2026-10-30 | AR Manager | 60 | Yes
AI-057 | Hire to Retire | Salary revision without HR approval evidence | Medium | In Progress | 2026-08-07 | 2026-11-05 | Payroll Lead | 54 | No
AI-058 | Procure to Pay | Duplicate vendor invoice paid without detection | Medium | Open | 2026-08-15 | 2026-11-13 | Head of Procurement | 46 | Yes
AI-059 | Financial Close | Close checklist sign-offs missing | High | Open | 2026-08-28 | 2026-10-27 | GL Lead | 33 | Yes
AI-060 | Fixed Assets | Disposals not removed from register | Critical | In Progress | 2026-09-03 | 2026-10-03 | Plant Accountant | 27 | Yes